## Start Here
Lowest-Cost Custom Quiz Website — Launch Checklist
This version replaces Tally and Make.com. You do not need coding skills: complete only the rows marked “You”; I can handle the technical rows after you approve each external account or live change.
Launch scope | Decision | Lowest-cost tool choices
Quiz at launch | One paid quiz | Existing DigitalOcean Droplet | Use the current Droplet | $0 extra server cost now | Already available
Customer account | No account / no Google login | Website + quiz + secure links | Custom lightweight Node website | $0 software licence | Built on your Droplet
Access | Secure emailed link valid for 7 days | Database | SQLite file + backup | $0 software licence | Enough for one-quiz launch
Result | Immediate result + retake during 7 days | Payment | Stripe Checkout | $0 fixed monthly; processing fees per sale | You own the Stripe account
History | No permanent answer or result history | Private email | Resend free tier | $0 at low launch volume | Use a verified domain
|  | SSL + web server | Caddy | $0 | Automatic HTTPS
|  | DNS / basic protection | Cloudflare free | $0 | Recommended
|  | Form / automation tools | No Tally, Make, or Zapier | $0 | Avoids recurring tool fees
Important: never paste passwords, Stripe secret keys, Resend keys, DigitalOcean API tokens, or SSH keys into this sheet or chat. Enter them yourself only in the relevant account or server environment.

## Your Setup Steps
Your Setup Steps — No Coding Required
Complete these in order. When a row says “Ready for Codex,” change its Status to Done and add only a safe confirmation or dashboard link in Evidence / Link — never a secret key.
Step | What you do | Simple instruction | Cost | Status | Evidence / Link | Ready for Codex?
1 | Choose the first quiz and price | Confirm quiz name, price/currency, and 10–15 questions. I can help write the questions. | $0 | Not started |  | Yes
2 | Choose support email | Pick the inbox customers can use for payment or access problems. | $0 | Not started |  | Yes
3 | Confirm GoDaddy domain access | Log in and confirm you can manage DNS records for the domain. | Already owned | Not started |  | Yes
4 | Create a Cloudflare account | Use the free plan. Add your domain; I will tell you exactly which DNS records to approve. | $0 | Not started |  | Yes
5 | Create a Stripe account | Use your own legal/business details and bank account. Keep test mode until we finish testing. | $0 fixed monthly | Not started |  | Yes
6 | Complete Stripe verification | Follow Stripe’s identity and bank verification prompts. This is required before payouts. | $0 | Not started |  | Yes
7 | Create a Resend account | Use the free transactional-email plan for access emails. | $0 at low volume | Not started |  | Yes
8 | Verify email domain in Resend | Resend will show DNS records. Add them in Cloudflare/GoDaddy; I can guide you. | $0 | Not started |  | Yes
9 | Confirm DigitalOcean dashboard access | Open the existing Droplet dashboard when we are ready. No need to share password or API token. | Existing server | Not started |  | Yes
10 | Approve website design and quiz content | Review the desktop/mobile screens and result copy before implementation. | $0 | Not started |  | Yes
11 | Approve test-to-live switch | After all tests pass, approve the final switch from Stripe test mode to live mode. | $0 | Not started |  | Yes

## Build and Test
Build and Test — Handled With You
Technical rows are shown so you know what is happening. I will not make external changes, publish the site, or turn on live payments without your approval.
Phase | Task | What it gives you | Handled by | Status | Your approval needed? | Test / evidence | Launch blocker?
Server | Create isolated quiz service | Keeps quiz data separate from OpenClaw on the same Droplet. | Codex | Not started | Yes |  | Yes
Server | Set up SQLite database and automated backup | Stores only purchase access, expiry, and temporary quiz data. | Codex | Not started | Yes |  | Yes
Server | Configure Caddy HTTPS and subdomain | Makes quiz.yourdomain.com secure with no SSL subscription. | Codex | Not started | Yes |  | Yes
Website | Build custom responsive landing page | Matches the selected dark editorial design on desktop and mobile. | Codex | Not started | Yes |  | Yes
Website | Build custom quiz screens | One question per screen, progress indicator, large answer buttons. | Codex | Not started | Yes |  | Yes
Payment | Connect Stripe Checkout in test mode | Customer pays before quiz access; browser redirect is never trusted as proof of payment. | Codex | Not started | Yes |  | Yes
Security | Verify Stripe webhook and create 7-day access | Only confirmed Stripe payment can issue an email-bound access record. | Codex | Not started | Yes |  | Yes
Email | Send access link through Resend | Customer receives expiry date and secure start button by email. | Codex | Not started | Yes |  | Yes
Security | Add email verification, rate limits, and link replacement | Reduces link-sharing and abuse; a resend invalidates the earlier unused link. | Codex | Not started | Yes |  | Yes
Result | Build result and retake page | Immediate result; retake stays available only before expiry. | Codex | Not started | Yes |  | Yes
Privacy | Delete temporary answers/results after seven days | No permanent customer quiz history at launch. | Codex | Not started | Yes |  | Yes
Test | Run Stripe test payment and failed-payment tests | Confirms one access email per successful payment and none after failure. | Joint | Not started | No |  | Yes
Test | Run link, expiry, retake, mobile, and browser tests | Checks the full customer journey, including an expired link and a forwarded link. | Joint | Not started | No |  | Yes
Launch | Run one small live payment | Final end-to-end proof after you approve live mode. | Joint | Not started | Yes |  | Yes