## Start Here
Paid Quiz Website — Setup Tracker
Use this checklist before launch. Update only the Status, Evidence / Link, and Notes columns. Never store API keys, passwords, card numbers, or private tokens here.
Launch readiness | Count | How to use this file
Total checklist items | 45 | 1. Complete account and domain tasks first.
Done | 0 | 2. Do all payment testing in Stripe test mode before going live.
Still to do | 45 | 3. Keep every customer link private and never record secrets here.
4. Mark each test Done only when you have evidence in the final column.
5. Switch to live mode only after every required line is Done.
Recommended MVP: custom secure quiz on your existing DigitalOcean Droplet + Stripe + Resend. Tally may be used for content drafting, but not as the protected access gate.

## Setup Checklist
Setup Checklist
Complete in order. “You” means you need to create, verify, or approve the account/change. “Codex” means I can prepare or implement it once you authorise access.
Phase | Task | Why it matters | Owner | Status | Evidence / Link | Notes | Required before launch?
Product | Confirm the launch offer | One quiz per purchase; price, currency, and 7-day access rule are final. | You | Not started |  |  | Yes
Product | Choose the first quiz and result categories | Defines the questions, scoring, result copy, and landing-page content. | Joint | Not started |  |  | Yes
Product | Write non-diagnostic disclaimer | Keeps personality/health-adjacent content clearly entertainment and self-reflection only. | Joint | Not started |  |  | Yes
Support | Choose a support email and response owner | Customers need a contact for access, payment, and refund issues. | You | Not started |  |  | Yes
Domain | Confirm GoDaddy domain ownership and login | Required to point a quiz subdomain to the website. | You | Not started |  |  | Yes
Domain | Create Cloudflare account | Provides free DNS, SSL support, and basic traffic protection. | You | Not started |  |  | Recommended
Domain | Choose the quiz subdomain | Example: quiz.yourdomain.com. Keep it stable before launch. | You | Not started |  |  | Yes
Payments | Create Stripe account (Hong Kong) | Collects payments and handles refunds. | You | Not started |  |  | Yes
Payments | Complete Stripe identity and bank verification | Stripe cannot pay out until required business details are verified. | You | Not started |  |  | Yes
Payments | Create one product and one price in Stripe | Keeps launch checkout simple; add more quizzes later. | Joint | Not started |  |  | Yes
Payments | Keep Stripe test and live modes separate | Prevents test payments or keys from reaching real customers. | Joint | Not started |  |  | Yes
Payments | Create signed Stripe webhook endpoint | The server, not the customer browser, confirms a successful payment. | Codex | Not started |  |  | Yes
Email | Create Resend account | Sends the 7-day private access email. | You | Not started |  |  | Yes
Email | Verify sending domain in Resend | Improves delivery and lets emails come from your domain. | You | Not started |  |  | Yes
Email | Publish SPF/DKIM DNS records | Required for email authentication and lower spam risk. | You | Not started |  |  | Yes
Server | Enable DigitalOcean backups | Allows recovery if the Droplet or database is damaged. | You | Not started |  |  | Recommended
Server | Create isolated quiz service and database | Keeps customer access data separate from OpenClaw. | Codex | Not started |  |  | Yes
Server | Configure HTTPS reverse proxy | Makes quiz.yourdomain.com secure and publicly reachable. | Codex | Not started |  |  | Yes
Server | Review firewall and service separation | Only web ports should be public; OpenClaw must stay isolated. | Joint | Not started |  |  | Yes
Server | Store secrets in server environment variables | Never place private keys in source code or this sheet. | Codex | Not started |  |  | Yes
Build | Create landing page | Explains the quiz, price, privacy, and purchase call to action. | Codex | Not started |  |  | Yes
Build | Build secure access-link flow | Creates email-bound, expiring access after confirmed payment. | Codex | Not started |  |  | Yes
Build | Build quiz questions and score logic | Shows one question per screen and calculates result server-side. | Joint | Not started |  |  | Yes
Build | Build result and retake experience | Shows the latest result and enables retake before expiry. | Codex | Not started |  |  | Yes
Privacy | Set 7-day deletion job | Deletes temporary quiz answers and results after access ends. | Codex | Not started |  |  | Yes
Privacy | Separate purchase records from quiz answers | Keeps accounting data apart from sensitive self-reflection responses. | Codex | Not started |  |  | Yes
Privacy | Set marketing consent to opt-in only | A purchase email is not automatic permission for marketing. | Codex | Not started |  |  | Yes
Operations | Set uptime and error alerts | Lets you know if payment emails or access links fail. | Codex | Not started |  |  | Recommended
Operations | Write refund and access-support process | Makes payment disputes and expired-link requests consistent. | Joint | Not started |  |  | Yes

## Testing Checklist
Testing Checklist
Run every test in Stripe test mode first. Mark Done only after you record the result or evidence. Repeat the final “live payment” test with a real small payment before public launch.
Area | Test | Expected result | Who runs it | Status | Actual result | Evidence / Link | Launch blocker?
Payment | Successful Stripe test payment | One paid access record is created and one access email is sent. | Joint | Not started |  |  | Yes
Payment | Failed or cancelled payment | No access link or active access record is created. | Joint | Not started |  |  | Yes
Payment | Duplicate webhook delivery | The same payment does not create a second paid access record. | Codex | Not started |  |  | Yes
Email | Access email delivery | Email arrives with correct sender, quiz name, and expiry time. | Joint | Not started |  |  | Yes
Email | Resend access email | A new link works and the earlier unused link stops working. | Joint | Not started |  |  | Yes
Access | Open link on purchaser device | Quiz opens after secure session is created. | Joint | Not started |  |  | Yes
Access | Open forwarded link on another device | New device must verify the purchaser email; no email means no access. | Joint | Not started |  |  | Yes
Access | Expired link | After seven days, customer sees expiry message and cannot see quiz/result. | Codex | Not started |  |  | Yes
Quiz | Complete quiz and receive result | Score and result display immediately with disclaimer. | Joint | Not started |  |  | Yes
Quiz | Retake during seven-day window | Customer can retake; newest temporary result replaces prior one. | Joint | Not started |  |  | Yes
Privacy | Automatic data deletion | Temporary answers/results are removed after expiry; payment record remains separate. | Codex | Not started |  |  | Yes
Security | Invalid token and repeated code attempts | Invalid requests are blocked or rate-limited; no secrets exposed. | Codex | Not started |  |  | Yes
Experience | Mobile test | Landing, checkout, quiz, result, and retake work on a phone browser. | Joint | Not started |  |  | Yes
Experience | Desktop browser test | Flow works on current Chrome and Safari/Edge. | Joint | Not started |  |  | Yes
Operations | Backup and recovery check | Database backup exists and recovery instructions are documented. | Codex | Not started |  |  | Recommended
Production | One real small live payment | Live payment, email, access, retake, and refund/support workflow all work. | You | Not started |  |  | Yes